## Master Plan
Sr No | Module | Epics | Total Stories |  | Backlog |  | Development |  | QA |  | Review |  | Release Done |  | Sprint 0 ( 9 Sep - 21 Sep ) |  |  |  | Sprint 1 (23 Sep - 5 Oct ) |  |  |  | Sprint 2 (7Oct - 19 Oct )
[15 empty] | Planned | Development | Under Review | Delivered | Planned | Development | Under Review | Delivered | Planned | Development | Under Review | Delivered
|  |  | Count | Effort (Day Wise) | Count | Effort (Day Wise) | Count | Effort (Day Wise) | Count | Effort (Day Wise) | Count | Effort (Day Wise) | Count | Effort (Day Wise) | Team Capacity : |  | Team Velocity : |  | Team Capacity : |  | Team Velocity : |  | Team Capacity : |  | Team Velocity :
1 | Admin | Adminstration | 25 | 75 | 5 | 15 | 3 | 9 |  |  | 3 | 9 | 14 | 42
2 | Design | Documentation | 13 | 196 | 3 | 56 | 2 | 30 |  |  | 2 | 30 | 6 | 80
3 | Scaffolding | Java - Scaffolding | 9 | 11 | 5 | 8 | [6 empty] | 4 | 3
4 | Utility | Java Services | 14 | 181 | 0 | 0 | 2 | 55 |  |  | 12 | 126 | [9 empty] | 13 | 1 |  | 7
5 | ePay Application | Transaction - Customer Creation | 9 | 104 | 7 | 64 | 2 | 40
6 | ePay Application | Transaction - Order Creation | 7 | 64 | 7 | 64
7 | ePay Application | Transaction - Transaction Initation | 15 | 141 | 15 | 141
8 | ePay Application | Payments - UPI | 6 | 55 | 6 | 55
9 | ePay Application | Payments - QR Code | 6 | 33 | 6 | 33
10 | ePay Application | Payments - SBI | 9 | 66 | 9 | 66
11 | ePay Application | Payments - Other INB | 8 | 75 | 8 | 75
12 | ePay Application | Payments - Cards | 15 | 84 | 15 | 84
13 | SDK | SDK - Java | 10 | 50 | 10 | 50
14 | Merchant Application | Merchant Services | 17 | 315 | 17 | 315
15 | SDK | SDK - Android | 10 | 65 | 10 | 61 | 2 | 4
16 | SDK | SDK - IOS | 10 | 65 | 10 | 61 | 2 | 4
17 | SDK | SDK- React Native | 10 | 65 | 10 | 61 | 2 | 4
18 | SDK | SDK- Flutter | 10 | 65 | 10 | 65
19 | Scaffolding | UI/Mobile - Scaffolding | 6 | 10 | 6 | 2 | 5 | 8
20 | ePay Application | ePay Transaction Portal | 9 | 95 | 9 | 77 | 1 | 18
21 | Merchant Application | Merchant Portal | 19 | 346 | 19 | 346
Totals |  |  | 237 | 2161 | 187 | 1699 | 21 | 172 | 0 | 0 | 17 | 165 | 24 | 125

## Module Planning
Module | Total SP | Backlog(SP) | Development(SP) | Review (SP) | Ready to Deploy / Done (SP)
System Setup | 75 | 15 | 9 | 9 | 42
Design | 196 | 56 | 30 | 30 | 80
Scaffolding | 21 | 10 | 8 | 0 | 3
Utilities | 181 | 0 | 55 | 126 | 0
ePay Application | 717 | 659 | 58 | 0 | 0
SDK | 310 | 298 | 12 | 0 | 0
Merchant Application | 661 | 661 | 0 | 0 | 0
Total | 2161 | 1699 | 172 | 165 | 125

## Sprint Planning
Sprint Planning | Start Date | End Date | Java (1179 SP) |  | UI (441 SP) |  | Mobile (270 SP) |  | QA (2161 SP - 237 Story)
|  |  | Developers | Capacity | Developers | Capacity | Developers | Capacity | QA (2161 SP - 237 Story) | Story Wise Capacity
Sprint 0 - 2 | 2024-09-09 | 2024-10-19 | 4 - 7 | 126 | 1 | 18 | 7 | 20 | 1
Sprint 3 | 2024-10-22 | 2024-11-11 | 7 | 105 | 1 | 15 | 7 | 105 | 10 | 50
Sprint 4 | 2024-11-12 | 2024-12-02 | 24 | 360 | 8 | 120 | 7 | 105 | 10 | 60
Sprint 5 | 2024-12-03 | 2024-12-23 | 24 | 360 | 10 | 150 | 7 | 105 | 10 | 70
Sprint 6 | 2024-12-24 | 2025-01-06 | 24 | 240 | 10 | 150 |  |  | 10 | 70
Development Path to Green
[11 empty] | Tech | Current Developers | PO - 1 | PO - 2 | PO - 3 | PO - 4 | Comments
[11 empty] | Java | 7 | 0 | Approved - 13 Deployed - 7 Yet to Deployed - 6 | Approved - 11 Deployed - 0 Yet to Deployed - 6 | NA
[11 empty] | UI | 1 | 1 | Approved - 6 Hold - 6 | 0 | Need Approval - 4 | Need new Approval and open the Hold position
[11 empty] | Mobile | 4 | 4 | Approved - 3 Deployed - 3 | NA | NA
[11 empty] | QA | 1 | 0 | Approved - 3 Hold - 2 | Approved - 3 Deployed - 0 Yet to Deployed - 3 | Need Approval - 8 | Need new Approval and open the Hold position

## Rough
Service/EPIC | Backlog | In Development | In Review | Done | Grand Total
Android-SDK | 32 | 1 | 1 |  | 34
ePay Transaction Portal | 8 | 1 |  |  | 9
ETL Utility / Golden Gate |  | 1 |  |  | 1
Flutter-SDK | 34 |  |  |  | 34
IOS-SDK | 33 |  | 1 |  | 34
Java Utilities | 1 | 1 | 12 |  | 14
Java-SDK | 6 |  |  |  | 6
Java-SDK | 1 |  |  |  | 1
Key Database |  | 1 |  |  | 1
Merchant Database | 1 |  |  |  | 1
Merchant Portal | 18 |  |  |  | 18
Merchant Service | 16 |  |  |  | 16
Old and New DB Synch Up | 1 |  |  |  | 1
Payment Service | 9 |  |  |  | 9
React Native-SDK | 33 |  | 1 |  | 34
Report Service | 1 |  |  |  | 1
Rule Database | 1 |  |  |  | 1
Rule Service | 3 |  |  |  | 3
Scalfolding | 2 | 7 | 2 | 4 | 15
System Setup | 3 | 2 | 7 | 12 | 24
Transaction Database | 1 |  |  |  | 1
Transaction Service | 22 | 2 |  |  | 24
Grand Total | 226 | 16 | 24 | 16 | 282

## Project Sheet
Sr No | Technology | BRD Ref | FSD Ref | TDD Ref | Story No | Status | Service/EPIC | Business Project | Task Details | Action Role | Review Role | Sprint | Start Date | End Date | DI - Dev Efforts | DI - Review Efforts | DI - Automation Efforts | DI - QA Efforts | SI - QA Efforts | SI - Bug Fix Efforts | UAT - QA Efforts | UAT - Bug Fix Efforts | Total Efforts | Remarks | Development+Test
1 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | In Development | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Transaction Service | Java Developers | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 | 1. Base Package Creation 2. Boiller code(DB connectivity, Flow Controller to DB, Liquibase Configuration, Sprintboot Configuration, Junit confirguration. All Springs Framework confirguration like authenticatio, validation, scheduler, DB creation, Listeners etc. | 0.75
2 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | In Development | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Payment Seervice | Java Developers | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
3 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | In Development | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Merchant Service | Java Developers | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
4 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | Backlog | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Rule Service | Architect - Java | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
5 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | Done | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Authentication Service | Architect - Java | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
6 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | Done | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Logging Service | Architect - Java | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
7 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | Done | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Notification Service | Architect - Java | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
8 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | Done | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Encryption Service | Architect - Java | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
9 | Java | BR-CO1 | FS_CO1 | TD_CO1 |  | In Development | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Java SDK | Java Developers | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.25 | 0.25 | [6 empty] | 0.5 |  | 0.5
10 | React | BR-CO1 | FS_CO1 | TD_CO1 |  | Backlog | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Merchant Portal | Architect-UI | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
11 | React | BR-CO1 | FS_CO1 | TD_CO1 |  | In Development | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Transaction Portal | Architect-UI | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
12 | React Native | BR-CO1 | FS_CO1 | TD_CO1 |  | In Review | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Transaction Portak SDK React Native | Architect-UI | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
13 | Flutter | BR-CO1 | FS_CO1 | TD_CO1 |  | In Development | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Transaction Portak SDK Flutter | Architect-UI | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
14 | iOS | BR-CO1 | FS_CO1 | TD_CO1 |  | In Development | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Transaction Portak SDK iOS | Architect-UI | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
15 | Android | BR-CO1 | FS_CO1 | TD_CO1 |  | In Review | Scaffolding | Transaction & Payment Page​ | Project Structure Creation - Transaction Portak SDK Android | Architect-UI | Solutiion Architect | Sprint 0 | 2024-09-09 | 2024-09-21 | 0.5 | 0.25 | [6 empty] | 0.75 |  | 0.75
16 | Database | BR-DB1 | FS_DB1 | TD_DB1 |  | In Development | Transaction Database | Transaction & Payment Page​ | Transaction Database creation by Liquibase | Architect - Java | Solutiion Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 4 | 0.8 | [6 empty] | 4.8 |  | 4.8
17 | Database | BR-DB1 | FS_DB1 | TD_DB2 |  | Backlog | Rule Database | Transaction & Payment Page​ | Rule Database creation by Liquibase | Architect - Java | Solutiion Architect | Sprint 1...Sprint 7 | 2024-10-15 | 2024-12-31 | 4 | 0.8 | [6 empty] | 4.8 |  | 4.8
18 | Database | BR-DB1 | FS_DB1 | TD_DB3 |  | Backlog | Merchant Database | Merchant Portal | Merchant Database creation by Liquibase | Architect - Java | Solutiion Architect | Sprint 1...Sprint 7 | 2024-10-15 | 2024-12-31 | 4 | 0.8 | [6 empty] | 4.8 |  | 4.8
19 | Database | BR-DB1 | FS_DB1 | TD_D4 |  | In Development | Key Database | Transaction & Payment Page​ | Key Database Creation by Liquibase | Architect - Java | Solutiion Architect | Sprint 1...Sprint 7 | 2024-10-15 | 2024-12-31 | 1 | 0.2 | [6 empty] | 1.2 |  | 1.2
20 | Java | BR-1 | FS_TX1 | TD_TX1 |  | In Development | Transaction Service | Transaction & Payment Page​ | Token Generation - Generate | Java Developers | Architect-Java | Sprint 1 | 2024-10-07 | 2024-10-19 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
21 | Java | BR-1 | FS_TX1 | TD_TX1 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Token Generation - Invalidate | Java Developers | Architect-Java | Sprint 1 | 2024-10-07 | 2024-10-19 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
22 | Java | BR-1 | FS_TX1 | TD_TX1 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Token Generation - Scheduler | Java Developers | Architect-Java | Sprint 1 | 2024-10-07 | 2024-10-19 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
23 | Java | BR-1 | FS_TX1 | TD_TX1 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Token Generation - Get all with Filters like Merchant ID, Request type wise, date wise | Java Developers | Architect-Java | Sprint 1 | 2024-10-07 | 2024-10-19 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
24 | Java | BR-1 | FS_TX2 | TD_TX2 |  | In Development | Transaction Service | Transaction & Payment Page​ | Merchant Customer Mapping - Creation | Java Developers | Architect-Java | Sprint 1 | 2024-10-07 | 2024-10-19 | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
25 | Java | BR-1 | FS_TX2 | TD_TX2 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Merchant Customer Mapping - Get Customer | Java Developers | Architect-Java | Sprint 1 | 2024-10-07 | 2024-10-19 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
26 | Java | BR-1 | FS_TX2 | TD_TX2 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Merchant Customer Mapping - Get all with all filters | Java Developers | Architect-Java | Sprint 1 | 2024-10-21 | 2024-11-02 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
27 | Java | BR-1 | FS_TX2 | TD_TX2 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Merchant Customer Mapping - Active/Inactive | Java Developers | Architect-Java | Sprint 1 | 2024-10-21 | 2024-11-02 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
28 | Java | BR-1 | FS_TX2 | TD_TX2 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Merchant Customer Mapping - Delete Customer | Java Developers | Architect-Java | Sprint 1 | 2024-10-21 | 2024-11-02 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
29 | Java | BR-1 | FS_TX2 | TD_RS-1 |  | Backlog | Rule Service | Transaction & Payment Page​ | Merchant Customer Mapping - Business Validations | Java Developers | Architect-Java | Sprint 1 | 2024-10-21 | 2024-11-02 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
30 | Java | BR-1 | FS_TX3 | TD_TX3 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Order Management - Creation | Java Developers | Architect-Java | Sprint 1 | 2024-10-21 | 2024-11-02 | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
31 | Java | BR-1 | FS_TX3 | TD_TX3 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Order Management - Get All with the filters | Java Developers | Architect-Java | Sprint 1 | 2024-10-21 | 2024-11-02 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
32 | Java | BR-1 | FS_TX3 | TD_TX3 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Order Managemen - Get | Java Developers | Architect-Java | Sprint 1 | 2024-10-21 | 2024-11-02 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
33 | Java | BR-1 | FS_TX3 | TD_TX3 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Order Status - Update Status | Java Developers | Architect-Java | Sprint 2 | 2024-10-21 | 2024-11-02 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
34 | Java | BR-1 | FS_TX3 | TD_TX3 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Order Management - Expiration | Java Developers | Architect-Java | Sprint 2 | 2024-10-21 | 2024-11-02 | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
35 | Java | BR-1 | FS_TX3 | TD_RS-1 |  | Backlog | Rule Service | Transaction & Payment Page​ | Order Management - Business Validations | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
36 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Booking | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 | It will charge calculation, pay mode selection | 22
37 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Get | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
38 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Get all with filters | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
39 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - UPI | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
40 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - QR Code | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
41 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - UPI | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
42 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Channel Bank | Java Developers | Architect-Java | Sprint 5 | 2024-11-18 | 2024-11-30 | 20 | 4 | 6 | 6 | 6 | 2 | 6 | 2 | 52 |  | 44
43 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - SBI Net Banking | Java Developers | Architect-Java | Sprint 5 | 2024-11-18 | 2024-11-30 | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
44 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - SBI Net Banking | Java Developers | Architect-Java | Sprint 5 | 2024-11-18 | 2024-11-30 | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
45 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Channel Bank - Corporate | Java Developers | Architect-Java | Sprint 6 | 2024-12-02 | 2024-12-14 | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
46 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Cards | Java Developers | Architect-Java | Sprint 6 | 2024-12-02 | 2024-12-14 | 30 | 6 | 9 | 9 | 9 | 3 | 9 | 3 | 78 |  | 66
47 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Refund | Java Developers | Architect-Java | Sprint 6 | 2024-12-02 | 2024-12-14 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
48 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Cancellation | Java Developers | Architect-Java | Sprint 6 | 2024-12-02 | 2024-12-14 | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
49 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Get Status | Java Developers | Architect-Java | Sprint 6 | 2024-12-02 | 2024-12-14 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
50 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Update Status | Java Developers | Architect-Java | Sprint 6 | 2024-12-02 | 2024-12-14 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
51 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Downtime API | Java Developers | Architect-Java | Sprint 7 | 2024-12-16 | 2024-12-28 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
52 | Java | BR-1 | FS_TX4 |  |  | In Development | ETL Utility / Golden Gate | Transaction & Payment Page​ | Transaction Mangement - DB Views build up and synch up | Java Developers | Architect-Java | Sprint 7 | 2024-12-16 | 2024-12-28 | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 | Merchant Info, Charges, DownTime Payments | 33
53 | Java | BR-1 | FS_TX4 | TD_RS-1 |  | Backlog | Rule Service | Transaction & Payment Page​ | Transaction Mangement - Business Validation | Java Developers | Architect-Java | Sprint 7 | 2024-12-16 | 2024-12-28 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
54 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Payment Service | Transaction & Payment Page​ | Transaction Mangement - Push and Pull Services | Java Developers | Architect-Java | Sprint 7 | 2024-12-16 | 2024-12-28 | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
55 | React | BR-1 | FS_TX4 | TD_TX5 |  | In Development | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - SBI ePay Main page | React Developers | Architect-UI | Sprint 1, Sprin 2 | 2024-09-23 | 2024-10-19 | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
56 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - UPI | React Developers | Architect-UI | Sprint 3 | 2024-10-21 | 2024-11-02 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
57 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - QR Code | React Developers | Architect-UI | Sprint 3 | 2024-10-21 | 2024-11-02 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
58 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Wallet | React Developers | Architect-UI | Sprint 4 | 2024-11-04 | 2024-11-16 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
59 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Channel Bank | React Developers | Architect-UI | Sprint 4 | 2024-11-04 | 2024-11-16 | 6 | 1.2 | 1.8 | 1.8 | 1.8 | 0.6 | 1.8 | 0.6 | 15.6 |  | 13.2
60 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - SBI Net Banking | React Developers | Architect-UI | Sprint 5 | 2024-11-18 | 2024-11-30 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
61 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Challan | React Developers | Architect-UI | Sprint 5 | 2024-11-18 | 2024-11-30 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
62 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Corporate | React Developers | Architect-UI | Sprint 6 | 2024-12-02 | 2024-12-14 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
63 | React | BR-1 | FS_TX4 | TD_TX5 |  | Backlog | ePay Transaction Portal | Transaction & Payment Page​ | Transaction Mangement - Payment Initiation - Cards | React Developers | Architect-UI | Sprint 6 | 2024-12-02 | 2024-12-14 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
64 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Booking Form Posting | Java Developers | Architect-UI | Sprint 7 | 2024-12-16 | 2024-12-28 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
65 | Java | BR-1 | FS_TX4 | TD_TX4 |  | Backlog | Transaction Service | Transaction & Payment Page​ | Transaction Mangement - Expiration | Java Developers | Architect-UI | Sprint 7 | 2024-12-16 | 2024-12-28 | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
66 | Java | BR-2 | FS_SDK1 | TD_SDK-2 |  | Backlog | Java-SDK | Merchant Integration & SDK | Token Generation - Creation | Java Developers | Architect-Java | Sprint 2 | 2024-10-21 | 2024-11-02 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
67 | Java | BR-2 | FS_SDK1 | TD_SDK-2 |  | Backlog | Java-SDK | Merchant Integration & SDK | Token Generation - Invalidate | Java Developers | Architect-Java | Sprint 2 | 2024-10-21 | 2024-11-02 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
68 | Java | BR-2 | FS_SDK1 | TD_SDK-2 |  | Backlog | Java-SDK | Merchant Integration & SDK | Encryption Utility | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
69 | Java | BR-2 | FS_SDK2 | TD_SDK-2 |  | Backlog | Java-SDK | Merchant Integration & SDK | Merchant Customer Mapping - Creation | Java Developers | Architect-Java | Sprint 4 | 2024-11-04 | 2024-11-16 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
70 | Java | BR-2 | FS_SDK3 | TD_SDK-2 |  | Backlog | Java-SDK | Merchant Integration & SDK | Order Management - Creation | Java Developers | Architect-Java | Sprint 5 | 2024-11-18 | 2024-11-30 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
71 | Java | BR-2 | FS_SDK4 | TD_SDK-2 |  | Backlog | Java-SDK | Merchant Integration & SDK | Transaction Mangement - Initiation | Java Developers | Architect-Java | Sprint 5 | 2024-11-18 | 2024-11-30 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
72 | Java | BR-2 | FS_SDK6 | TD_SDK-2 |  | Backlog | Java-SDK | Merchant Integration & SDK | Transaction Status | Java Developers | Architect-Java | Sprint 6 | 2024-12-02 | 2024-12-14 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
73 | Android | BR-2 |  |  |  | In Review | Android-SDK | Merchant Integration & SDK | Utility Setup | Android Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
74 | Android | BR-2 |  |  |  | In Development | Android-SDK | Merchant Integration & SDK | Validation Service - Validate Payment URL Format | Android Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
75 | Android | BR-2 |  |  |  | In Development | Android-SDK | Merchant Integration & SDK | Validation Service - Validate Domain of Payment | Android Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
76 | Android | BR-2 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Validation Service - Validate Payment Data Hash in URL | Android Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
77 | Android | BR-2 |  |  |  | In Development | Android-SDK | Merchant Integration & SDK | Validation Service -Log Invalid Payment URL Attempts | Android Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
78 | Android | BR-2 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Validation Service - Display User-Friendly Error Messages for Payment URL Validation | Android Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
79 | Android | BR-2 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Validation Service - Check Network Connectivity in SDK | Android Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
80 | Android | BR-3 |  |  |  | In Development | Android-SDK | Merchant Integration & SDK | EpayWebview Implementation - Create Custom WebView | Android Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
81 | Android | BR-4 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EpayWebview Implementation - Navigation in EpayWebview | Android Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
82 | Android | BR-5 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EpayWebview Implementation - WebView Responsiveness and Media Rendering | Android Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
83 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EpayWebview Implementation - Override Navigation and Handle Custom URL Schemes | Android Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
84 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | Android Developer | UI - Architect | Sprint 3 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
85 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Establish Two-Way Communication | Android Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
86 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Handle Events Triggered from the WebView | Android Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
87 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Trigger Native SDK Features | Android Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
88 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Bridge Web and Mobile Functionality | Android Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
89 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | Android Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
90 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Create Transaction Activity Class | Android Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
91 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Load Payment Page in Custom WebView | Android Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
92 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Success Event | Android Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
93 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Failure Event | Android Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
94 | Android | BR-6 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Cancellation by the Customer | Android Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
95 | Android | BR-7 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Delegate JavaScript Events to EPayJsInterface | Android Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
96 | Android | BR-8 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Display Loading Indicator During Transaction | Android Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
97 | Android | BR-9 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Permission Manager Class | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
98 | Android | BR-10 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle SDK Permissions Efficiently | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
99 | Android | BR-11 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Utility Manager Class | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
100 | Android | BR-12 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK |  | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
101 | Android | BR-13 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Access Device and Network Information | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
102 | Android | BR-14 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Download Manager Class | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
103 | Android | BR-15 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Ensure Correct Challan Download Location | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
104 | Android | BR-16 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle UPI Payment Event | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
105 | Android | BR-17 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | Payment Journey Implementation - Open Selected UPI App from SDK | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
106 | Android | BR-18 |  |  |  | Backlog | Android-SDK | Merchant Integration & SDK | JSEvent Handler | Android Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
107 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Utility Setup | Flutter Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
108 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Validation Service - Validate Payment URL Format | Flutter Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
109 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Validation Service - Validate Domain of Payment | Flutter Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
110 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Validation Service - Validate Payment Data Hash in URL | Flutter Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
111 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Validation Service -Log Invalid Payment URL Attempts | Flutter Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
112 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Validation Service - Display User-Friendly Error Messages for Payment URL Validation | Flutter Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
113 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Validation Service - Check Network Connectivity in SDK | Flutter Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
114 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EpayWebview Implementation - Create Custom WebView | Flutter Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
115 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EpayWebview Implementation - Navigation in EpayWebview | Flutter Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
116 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EpayWebview Implementation - WebView Responsiveness and Media Rendering | Flutter Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
117 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EpayWebview Implementation - Override Navigation and Handle Custom URL Schemes | Flutter Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
118 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | Flutter Developer | UI - Architect | Sprint 3 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
119 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Establish Two-Way Communication | Flutter Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
120 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Handle Events Triggered from the WebView | Flutter Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
121 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Trigger Native SDK Features | Flutter Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
122 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Bridge Web and Mobile Functionality | Flutter Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
123 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | Flutter Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
124 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Create Transaction Activity Class | Flutter Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
125 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Load Payment Page in Custom WebView | Flutter Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
126 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Success Event | Flutter Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
127 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Failure Event | Flutter Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
128 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Cancellation by the Customer | Flutter Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
129 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Delegate JavaScript Events to EPayJsInterface | Flutter Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
130 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Display Loading Indicator During Transaction | Flutter Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
131 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Permission Manager Class | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
132 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle SDK Permissions Efficiently | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
133 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Utility Manager Class | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
134 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK |  | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
135 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Access Device and Network Information | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
136 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Download Manager Class | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
137 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Ensure Correct Challan Download Location | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
138 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle UPI Payment Event | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
139 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | Payment Journey Implementation - Open Selected UPI App from SDK | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
140 | Flutter | BR-2 |  |  |  | Backlog | Flutter-SDK | Merchant Integration & SDK | JSEvent Handler | Flutter Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
141 | iOS | BR-2 |  |  |  | In Review | IOS-SDK | Merchant Integration & SDK | Utility Setup | iOS Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
142 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Validation Service - Validate Payment URL Format | iOS Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
143 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Validation Service - Validate Domain of Payment | iOS Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
144 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Validation Service - Validate Payment Data Hash in URL | iOS Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
145 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Validation Service -Log Invalid Payment URL Attempts | iOS Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
146 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Validation Service - Display User-Friendly Error Messages for Payment URL Validation | iOS Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
147 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Validation Service - Check Network Connectivity in SDK | iOS Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
148 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EpayWebview Implementation - Create Custom WebView | iOS Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
149 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EpayWebview Implementation - Navigation in EpayWebview | iOS Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
150 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EpayWebview Implementation - WebView Responsiveness and Media Rendering | iOS Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
151 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EpayWebview Implementation - Override Navigation and Handle Custom URL Schemes | iOS Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
152 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | iOS Developer | UI - Architect | Sprint 3 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
153 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Establish Two-Way Communication | iOS Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
154 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Handle Events Triggered from the WebView | iOS Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
155 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Trigger Native SDK Features | iOS Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
156 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Bridge Web and Mobile Functionality | iOS Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
157 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | iOS Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
158 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Create Transaction Activity Class | iOS Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
159 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Load Payment Page in Custom WebView | iOS Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
160 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Success Event | iOS Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
161 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Failure Event | iOS Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
162 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Cancellation by the Customer | iOS Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
163 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Delegate JavaScript Events to EPayJsInterface | iOS Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
164 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Display Loading Indicator During Transaction | iOS Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
165 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Permission Manager Class | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
166 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle SDK Permissions Efficiently | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
167 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Utility Manager Class | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
168 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK |  | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
169 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Access Device and Network Information | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
170 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Download Manager Class | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
171 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Ensure Correct Challan Download Location | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
172 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle UPI Payment Event | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
173 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | Payment Journey Implementation - Open Selected UPI App from SDK | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
174 | iOS | BR-2 |  |  |  | Backlog | IOS-SDK | Merchant Integration & SDK | JSEvent Handler | iOS Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
175 | React Native | BR-2 |  |  |  | In Review | React Native-SDK | Merchant Integration & SDK | Utility Setup | React Native Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
176 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Validation Service - Validate Payment URL Format | React Native Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
177 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Validation Service - Validate Domain of Payment | React Native Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
178 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Validation Service - Validate Payment Data Hash in URL | React Native Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
179 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Validation Service -Log Invalid Payment URL Attempts | React Native Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
180 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Validation Service - Display User-Friendly Error Messages for Payment URL Validation | React Native Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
181 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Validation Service - Check Network Connectivity in SDK | React Native Developer | UI - Architect | Sprint 1 | 2024-09-23 | 2024-10-05 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
182 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EpayWebview Implementation - Create Custom WebView | React Native Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
183 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EpayWebview Implementation - Navigation in EpayWebview | React Native Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
184 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EpayWebview Implementation - WebView Responsiveness and Media Rendering | React Native Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
185 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EpayWebview Implementation - Override Navigation and Handle Custom URL Schemes | React Native Developer | UI - Architect | Sprint 2 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
186 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | React Native Developer | UI - Architect | Sprint 3 | 2024-10-07 | 2024-10-19 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
187 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Establish Two-Way Communication | React Native Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
188 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EPayJsInterface Implementation -Handle Events Triggered from the WebView | React Native Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
189 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Trigger Native SDK Features | React Native Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
190 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Bridge Web and Mobile Functionality | React Native Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
191 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | EPayJsInterface Implementation - Create EPayJsInterface Class | React Native Developer | UI - Architect | Sprint 3 | 2024-10-21 | 2024-11-02 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
192 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Create Transaction Activity Class | React Native Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
193 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Load Payment Page in Custom WebView | React Native Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
194 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Success Event | React Native Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
195 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Failure Event | React Native Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
196 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Handle Payment Cancellation by the Customer | React Native Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
197 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Transaction Activity Implementation -Delegate JavaScript Events to EPayJsInterface | React Native Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
198 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Transaction Activity Implementation - Display Loading Indicator During Transaction | React Native Developer | UI - Architect | Sprint 4 | 2024-11-04 | 2024-11-16 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
199 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Permission Manager Class | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
200 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle SDK Permissions Efficiently | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
201 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Utility Manager Class | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
202 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK |  | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
203 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Access Device and Network Information | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
204 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Create Download Manager Class | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
205 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Ensure Correct Challan Download Location | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
206 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Handle UPI Payment Event | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
207 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | Payment Journey Implementation - Open Selected UPI App from SDK | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 0.5 | 0.1 | 0.15 | 0.15 | 0.15 | 0.05 | 0.15 | 0.05 | 1.3 |  | 1.1
208 | React Native | BR-2 |  |  |  | Backlog | React Native-SDK | Merchant Integration & SDK | JSEvent Handler | React Native Developer | UI - Architect | Sprint 5 | 2024-11-18 | 2024-11-30 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
209 | Java | BR-4 | FS_JS4 | TD_JS-4 |  | In Review | Java Utilities | Transaction & Payment Page​ | Encryption Service-Encryption Utility | Architect - Java | Solutiion Architect | Sprint 2 | 2024-09-23 | 2024-10-05 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
210 | Java | BR-4 | FS_JS4 | TD_JS-4 |  | In Review | Java Utilities | Transaction & Payment Page​ | Encryption Service - Decryption Utility | Architect - Java | Solutiion Architect | Sprint 2 | 2024-09-23 | 2024-10-05 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
211 | Java | BR-4 | FS_JS3 | TD_JS-3 |  | In Review | Java Utilities | Transaction & Payment Page​ | Logging service - Logging Utility | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
212 | Java | BR-4 | FS_JS2 | TD_JS-2 |  | In Review | Java Utilities | Transaction & Payment Page​ | Notification Service- Email | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
213 | Java | BR-4 | FS_JS2 | TD_JS-2 |  | In Review | Java Utilities | Transaction & Payment Page​ | Notification Service - SMS | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
214 | Java | BR-4 | FS_JS2 | TD_JS-2 |  | In Review | Java Utilities | Transaction & Payment Page​ | Notification Service - Template Creation | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 6 | 1.2 | 1.8 | 1.8 | 1.8 | 0.6 | 1.8 | 0.6 | 15.6 |  | 13.2
215 | Java | BR-4 | FS_JS2 | TD_JS-2 |  | In Review | Java Utilities | Transaction & Payment Page​ | Notification Service - Kafka Consumer Creation | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
216 | Java | BR-4 | FS_JS1 | TD_JS-1 |  | In Review | Java Utilities | Transaction & Payment Page​ | Authentication Service - Token Generation | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
217 | Java | BR-4 | FS_JS1 | TD_JS-1 |  | In Review | Java Utilities | Transaction & Payment Page​ | Authentication Service - Token Authorization | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
218 | Java | BR-4 | FS_JS1 | TD_JS-1 |  | In Review | Java Utilities | Transaction & Payment Page​ | Authentication Service - Cors Origin SetUp | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
219 | Java | BR-4 | FS_JS1 | TD_JS-1 |  | In Review | Java Utilities | Transaction & Payment Page​ | Authentication Service - Whitelisting | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 2 | 0.4 | 0.6 | 0.6 | 0.6 | 0.2 | 0.6 | 0.2 | 5.2 |  | 4.4
220 | Java | BR-4 | FS_JS5 | TD_JS-5 |  | In Development | Java Utilities | Transaction & Payment Page​ | Encryption Service - Key Managment | Java Developers | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
221 | Java | BR-4 | FS_JS1 | TD_JS-1 |  | In Review | Java Utilities | Transaction & Payment Page​ | Authentication Service - Token validation | Architect - Java | Solutiion Architect | Sprint 3 | 2024-09-23 | 2024-10-05 | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
222 | Java | BR-3 | FS_MS_2 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Dashboard API | Java Developers | Architect - Java |  |  |  | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
223 | Java | BR-3 | FS_MS_8 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Business Profile Card | Java Developers | Architect - Java |  |  |  | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
224 | Java | BR-3 | FS_MS_3 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Admin Creation | Java Developers | Architect - Java |  |  |  | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
225 | Java | BR-3 | FS_MS_3 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Admin Updation | Java Developers | Architect - Java |  |  |  | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
226 | Java | BR-3 | FS_MS_1 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Patch API for role switiching, Active/Inactive | Java Developers | Architect - Java |  |  |  | 6 | 1.2 | 1.8 | 1.8 | 1.8 | 0.6 | 1.8 | 0.6 | 15.6 |  | 13.2
227 | Java | BR-3 | FS_MS_3 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Role Managmenet | Java Developers | Architect - Java |  |  |  | 6 | 1.2 | 1.8 | 1.8 | 1.8 | 0.6 | 1.8 | 0.6 | 15.6 |  | 13.2
228 | Java | BR-3 | FS_MS_1 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Login | Java Developers | Architect - Java |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
229 | Java | BR-3 | FS_MS_1 |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Reset and Forgot Password | Java Developers | Architect - Java |  |  |  | 4 | 0.8 | 1.2 | 1.2 | 1.2 | 0.4 | 1.2 | 0.4 | 10.4 |  | 8.8
230 | Java | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Service | Merchant Portal | Merchant Portal based filtering | Java Developers | Architect - Java |  |  |  | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
231 | Java | BR-3 | FS_MS_4 |  |  | Backlog | Merchant Service | Merchant Portal | View Settlement | Java Developers | Architect - Java |  |  |  | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
232 | Java | BR-3 | FS_MS_5 |  |  | Backlog | Merchant Service | Merchant Portal | View Invoices and Details | Java Developers | Architect - Java |  |  |  | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
233 | Java | BR-3 | FS_MS_6 |  |  | Backlog | Merchant Service | Merchant Portal | Refund Booking | Java Developers | Architect - Java |  |  |  | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
234 | Java | BR-3 | FS_MS_7 |  |  | Backlog | Merchant Service | Merchant Portal | Report Generation and Scheduler | Java Developers | Architect - Java |  |  |  | 12 | 2.4 | 3.6 | 3.6 | 3.6 | 1.2 | 3.6 | 1.2 | 31.2 |  | 26.4
235 | Java | BR-3 | FS_MS_9 |  |  | Backlog | Merchant Service | Merchant Portal | Order Tracking | Java Developers | Architect - Java |  |  |  | 9 | 1.8 | 2.7 | 2.7 | 2.7 | 0.9 | 2.7 | 0.9 | 23.4 |  | 19.8
236 | Java | BR-3 | FS_MS_10 |  |  | Backlog | Merchant Service | Merchant Portal | Transaction Search and Tracking | Java Developers | Architect - Java |  |  |  | 9 | 1.8 | 2.7 | 2.7 | 2.7 | 0.9 | 2.7 | 0.9 | 23.4 |  | 19.8
237 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Merchant Dashboard Role Based view | React Developers | Architect-UI |  |  |  | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
238 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Base Components | React Developers | Architect-UI |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
239 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Pagination Component | React Developers | Architect-UI |  |  |  | 3 | 0.6 | 0.9 | 0.9 | 0.9 | 0.3 | 0.9 | 0.3 | 7.8 |  | 6.6
240 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Listing Component | React Developers | Architect-UI |  |  |  | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
241 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Filtering Component | React Developers | Architect-UI |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
242 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Form Component | React Developers | Architect-UI |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
243 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Menu Creation | React Developers | Architect-UI |  |  |  | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
244 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Role Base Access Managment | React Developers | Architect-UI |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
245 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Multilingual setup | React Developers | Architect-UI |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
246 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Theme based UI Creation | React Developers | Architect-UI |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
247 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Login, Reset and Forgot Password | React Developers | Architect-UI |  |  |  | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
248 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Merchant Admin (Listing, Add/Edit/Filteting) | React Developers | Architect-UI |  |  |  | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
249 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Merchant Role Based Access Add/Edit | React Developers | Architect-UI |  |  |  | 8 | 1.6 | 2.4 | 2.4 | 2.4 | 0.8 | 2.4 | 0.8 | 20.8 |  | 17.6
250 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Transaction Listing/Filtering/Refund/Cancellation | React Developers | Architect-UI |  |  |  | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
251 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Customer Listing/Filtering/Refund/Cancellation | React Developers | Architect-UI |  |  |  | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
252 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Order Listing/Filtering/Refund/Cancellation | React Developers | Architect-UI |  |  |  | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
253 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Reports | React Developers | Architect-UI |  |  |  | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
254 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Portal | Merchant Portal | Notifications | React Developers | Architect-UI |  |  |  | 5 | 1 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 0.5 | 13 |  | 11
255 | React | BR-3 | FS_MP1- Dashboard |  |  | Backlog | Merchant Service | Merchant Portal | Buffer Time | React Developers | Architect-UI |  |  |  | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
256 | Database | BR-DB1 | FS_DB5 |  |  | Backlog | Old and New DB Synch Up | Transaction & Payment Page​ |  | Architect - Java | Architect - Java |  |  |  | 15 | 3 | 4.5 | 4.5 | 4.5 | 1.5 | 4.5 | 1.5 | 39 |  | 33
257 | Report | BR-RS | FS_RS1 |  |  | Backlog | Report Service | Merchant Portal |  | Java Developers | Architect - Java |  |  |  | 25 | 5 | 7.5 | 7.5 | 7.5 | 2.5 | 7.5 | 2.5 | 65 |  | 55
258 | Java |  |  |  |  | In Development | Java Utilities | R&D | Hazlecast Implementation | Java Developers | Solutiion Architect | Sprint 3 | 2024-10-21 | 2024-10-31 | 10 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 26 |  | 22
259 | System |  |  |  |  | Backlog | System Setup | Administration | Ranu Jain | individual | CEdge Admin | [13 empty] | 0
260 | System |  |  |  |  | Done | System Setup | Administration | Binoy | individual | CEdge Admin
261 | System |  |  |  |  | Done | System Setup | Administration | Faizan | individual | CEdge Admin
262 | System |  |  |  |  | Backlog | System Setup | Administration | Sandeep D | individual | CEdge Admin | [13 empty] | 0
263 | System |  |  |  |  | Done | System Setup | Administration | Harshil K | individual | CEdge Admin
264 | System |  |  |  |  | Backlog | System Setup | Administration | Sandeep S | individual | CEdge Admin | [13 empty] | 0
265 | System |  |  |  |  | Done | System Setup | Administration | Devendra | individual | CEdge Admin
266 | System |  |  |  |  | Done | System Setup | Administration | Hrishikesh | individual | CEdge Admin
267 | System |  |  |  |  | Done | System Setup | Administration | Shilpa | individual | CEdge Admin
268 | System |  |  |  |  | Done | System Setup | Administration | Bhushan | individual | CEdge Admin
269 | System |  |  |  |  | Done | System Setup | Administration | Rahul | individual | CEdge Admin
270 | System |  |  |  |  | Done | System Setup | Administration | Harikrishna | individual | CEdge Admin
271 | System |  |  |  |  | Done | System Setup | Administration | Nirvay | individual | CEdge Admin
272 | System |  |  |  |  | Done | System Setup | Administration | Ranjan | individual | CEdge Admin
273 | System |  |  |  |  | In Development | System Setup | Administration | Poonam | individual | CEdge Admin | [13 empty] | 0
274 | System |  |  |  |  | In Development | System Setup | Administration | Sarita | individual | CEdge Admin | [13 empty] | 0
275 | System |  |  |  |  | In Review | System Setup | Administration | Ritesh | individual | CEdge Admin | [13 empty] | 0
276 | System |  |  |  |  | In Review | System Setup | Administration | Lincy | individual | CEdge Admin | [13 empty] | 0
277 | System |  |  |  |  | In Review | System Setup | Administration | Palash | individual | CEdge Admin | [13 empty] | 0
278 | System |  |  |  |  | In Review | System Setup | Administration | HariOm | individual | CEdge Admin | [13 empty] | 0
279 | System |  |  |  |  | In Review | System Setup | Administration | Harishil | individual | CEdge Admin | [13 empty] | 0
280 | System |  |  |  |  | In Review | System Setup | Administration | Amit Kumar | individual | CEdge Admin | [13 empty] | 0
281 | System |  |  |  |  | In Review | System Setup | Administration | Lokendra | individual | CEdge Admin | [13 empty] | 0
282 | System |  |  |  |  | Done | System Setup | Administration | Sagar | individual | CEdge Admin
283
284
285
286
287
288
289
1

## Sprint - 0
Sprint 0
Start Date | 2024-09-09
End Date | 2024-09-21
Status | Complete
Delivery Team | 15
Managment Team | 4
Total Team | 19
Delivery Team |  |  |  | Managment Team
Team | Resource Count | Capacity | Velocity | Team | Resource Count
Java Team | 2 | 16 | 0 | PM | 1
Mobile Team | 4 | 32 | 0 | DM | 1
UI Team | 1 | 8 | 0 | Architect | 1
Product Team | 2 | 16 | 0 | Lead | 1
DevOps Team |  | 0 | 0
Total Team | 9 | 72 | 0 |  | 4
Sr No | Team | BRD Ref | FSD Ref | TDD Ref | Story No | Service/EPIC | Task Details | SP | Assignee | Status | Delayed | nETA | Actual End Date | Comments
1 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Transaction Service | 1 | Shilpa | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
2 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Payment Seervice | 1 | Shilpa | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
3 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Merchant Service | 1 | Rahul | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
4 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Rule Service | 1 | Sandeep | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
5 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Authentication Service | 1 | Shilpa | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
6 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Logging Service | 1 | HariKrishna | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
7 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Notification Service | 1 | Bhushan | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
8 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Encryption Service | 1 | Hrishikesh | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
9 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Java SDK | 0.5 | Rahul | InProgress | 17 Days | 2024-10-18
10 | UI Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - Transaction Portal |  | Sagar | InReview | 16 Days | 2024-10-16 | 2024-10-16 | System has been recived on - 3 Sep Git access has been recived on -
11 | Mobile Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - SDK React Native |  | Lincy | InProgress | 17 Days | 2024-10-18 | 2024-09-21 | System has been recived on - 3 Sep Git access has been recived on -
12 | Mobile Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - SDK Flutter |  | Hariom | InProgress | 17 Days | 2024-10-18 | 2024-09-21 | System has been recived on - 3 Sep Git access has been recived on -
13 | Mobile Team | BR-CO1 | FS_CO1 | TD_CO1 |  | Scalfolding | Project Structure Creation - SDK Android |  | Ritesh | InProgress | 17 Days | 2024-10-18 | 2024-09-21 | System has been recived on - 3 Sep Git access has been recived on -
14 | Mobile Team |  |  |  |  | Documentation | Reading TDD and working on POC - SDK iOS |  | Amit/Harshil/Lokendra | Done |  |  | 2024-09-21

## Sprint - 1
Sprint 0
Start Date | 2024-09-23
End Date | 2024-10-05
Status | Complete
Delivery Team | 17
Managment Team | 4
Total Team | 21
Delivery Team |  |  |  | Managment Team
Team | Resource Count | Capacity | Velocity | Team | Resource Count
Java Team | 6 | 48 | 0 | PM | 1
Mobile Team | 7 | 56 | 0 | DM | 1
UI Team | 1 | 8 | 0 | Architect | 1
Product Team | 2 | 16 | 0 | Lead | 1
DevOps Team | 1 | 8 | 0
Total Team | 17 | 136 | 0 |  | 4
Sr No | Team | BRD Ref | FSD Ref | TDD Ref | Spill Over Sprints | Story No | Service/EPIC | Task Details | SP | Assignee | Status | Delayed | nETA | Actual End Date | Comments
1 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | Shilpa | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
2 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | Shilpa | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
3 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | Rahul | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
4 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | Sandeep | InProgress | 17 Days | 2024-10-18 |  | Need to move in Git lab and Review need to complete
5 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | Shilpa | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
6 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | HariKrishna | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
7 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | Bhushan | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
8 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 1 | Hrishikesh | Done | 8 Days | 2024-10-03 | 2024-10-03 | System has been recived on - 27 Sep Git access has been recived on -
9 | Java Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  |  |  | 0.5 | Rahul | InProgress | 17 Days | 2024-10-18
10 | UI Team | BR-1 | FS_TX4 | TD_TX5 |  |  | ePay Transaction Portal | Transaction Mangement - SBI ePay Main page |  | Sagar | InProgress | 17 Days | 2024-10-31 |  | System has been recived on - 3 Sep Git access has been recived on -
11 | Mobile Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  | Scalfolding | Project Structure Creation - SDK React Native |  | Lincy | InProgress | 17 Days | 2024-10-18 | 2024-10-05 | System has been recived on - 3 Sep Git access has been recived on -
12 | Mobile Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  | Scalfolding | Project Structure Creation - SDK Flutter |  | Hariom | InProgress | 17 Days | 2024-10-18 | 2024-10-05 | System has been recived on - 3 Sep Git access has been recived on -
13 | Mobile Team | BR-CO1 | FS_CO1 | TD_CO1 |  |  | Scalfolding | Project Structure Creation - SDK Android |  | Ritesh | InProgress | 17 Days | 2024-10-18 | 2024-10-05 | System has been recived on - 3 Sep Git access has been recived on -
14 | Mobile Team | [5 empty] | Documentation | Reading TDD and working on POC - SDK iOS |  | Amit/Harshil/Lokendra | Done |  |  | 2024-10-05
15 | Mobile Team | [5 empty] | System Setup | System setup - Android/Flutter/ReactNative team |  | Mobile Team | InProgress |  |  | 2024-10-05 | System has been recived on - 3 Sep Git access has been recived on -

## Sprint - 2
Sprint 0
Start Date | 2024-10-07
End Date | 2024-10-19
Status | InProgress
Delivery Team | 18
Managment Team | 5
Total Team | 23
Delivery Team |  |  |  | Managment Team
Team | Resource Count | Capacity | Velocity | Team | Resource Count
Java Team | 6 | 48 | 0 | PM | 1
Mobile Team | 7 | 56 | 0 | DM | 1
UI Team | 1 | 8 | 0 | Architect | 2
Product Team | 3 | 24 | 0 | Lead | 1
DevOps Team | 1 | 8 | 0
Total Team | 18 | 144 | 0 |  | 5
Sr No | Team | BRD Ref | FSD Ref | TDD Ref | Spill Over Sprints | Story No | Service/EPIC | Task Details | SP | Assignee | Status | Delayed | nETA | Actual End Date | Comments
1 | Java Team
2 | Java Team
3 | Java Team
4 | Java Team
5 | Java Team
6 | Java Team
7 | Java Team
8 | Java Team
9 | Java Team
10 | UI Team | BR-1 | FS_TX4 | TD_TX5 |  |  | ePay Transaction Portal | Transaction Mangement - SBI ePay Main page |  | Sagar | InProgress | 17 Days | 2024-10-31 |  | System has been recived on - 3 Sep Git access has been recived on -
11 | Mobile Team | [5 empty] | System Setup | System setup - Android |  | Sandip/Ritesh/Palash | Done |  |  | 2024-10-19
12 | Mobile Team | [5 empty] | System Setup | System setup - Flutter |  | Hariom/Harshil | InProgress |  |  | 2024-10-19
13 | Mobile Team | [5 empty] | System Setup | System setup - React Native |  | Lincy | Done |  |  | 2024-10-19
14 | Mobile Team | [5 empty] | System Setup | System setup - iOS |  | Amit/Lokendra | Done |  |  | 2024-10-19
15 | Mobile Team | [5 empty] | Scalfolding | Project Structure Creation - SDK iOS |  | Lokendra | Done |  |  | 2024-10-19

## Sheet1
Count of Status | Status
Service/EPIC | Backlog | Done | In Development | In Review | (blank) | Grand Total
Android-SDK | 32 |  | 1 | 1 |  | 34
ePay Transaction Portal | 8 |  | 1 |  |  | 9
ETL Utility / Golden Gate |  |  | 1 |  |  | 1
Flutter-SDK | 34 |  |  |  |  | 34
IOS-SDK | 33 |  |  | 1 |  | 34
Java Utilities | 1 |  | 1 | 12 |  | 14
Java-SDK | 6 |  |  |  |  | 6
Java-SDK | 1 |  |  |  |  | 1
Key Database |  |  | 1 |  |  | 1
Merchant Database | 1 |  |  |  |  | 1
Merchant Portal | 18 |  |  |  |  | 18
Merchant Service | 16 |  |  |  |  | 16
Old and New DB Synch Up | 1 |  |  |  |  | 1
Payment Service | 9 |  |  |  |  | 9
React Native-SDK | 33 |  |  | 1 |  | 34
Report Service | 1 |  |  |  |  | 1
Rule Database | 1 |  |  |  |  | 1
Rule Service | 3 |  |  |  |  | 3
Scalfolding | 2 | 4 | 7 | 2 |  | 15
System Setup | 3 | 12 | 2 | 7 |  | 24
Transaction Database | 1 |  |  |  |  | 1
Transaction Service | 22 |  | 2 |  |  | 24
(blank)
Grand Total | 226 | 16 | 16 | 24 |  | 282

## Sprint - 3
Sprint 0
Start Date | 2024-10-07
End Date | 2024-10-19
Status | InProgress
Delivery Team | 18
Managment Team | 5
Total Team | 23
Delivery Team |  |  |  | Managment Team
Team | Resource Count | Capacity | Velocity | Team | Resource Count
Java Team | 6 | 48 | 0 | PM | 1
Mobile Team | 7 | 56 | 0 | DM | 1
UI Team | 1 | 8 | 0 | Architect | 2
Product Team | 3 | 24 | 0 | Lead | 1
DevOps Team | 1 | 8 | 0
Total Team | 18 | 144 | 0 |  | 5
Sr No | Team | BRD Ref | FSD Ref | TDD Ref | Spill Over Sprints | Story No | Service/EPIC | Task Details | SP | Assignee | Status | Delayed | nETA | Actual End Date | Comments
1 | Java Team
2 | Java Team
3 | Java Team
4 | Java Team
5 | Java Team
6 | Java Team
7 | Java Team
8 | Java Team
9 | Java Team